## Read Me
GreenThreads Operations — Denver Launch Readiness (v2)
HW#3 Data Intelligence Project — supporting analysis. Revised with cross-department source data.
Company: GreenThreads ¦ Function: Operations ¦ Analysis date (As_of_Date): August 18, 2026
Function goal (HW#1): get the four launch products onto the Denver sales floor on time.
What changed in v2
v1 analyzed supplier reliability against an October 12 opening treated as fixed. Finance and HR source
documents show that date is not established anywhere: the lease build-out window ends Oct 13-27, and no
document in any department states a required in-store date. Timeline risk is now the lead finding, with
supplier reliability as the exposure that rides on it.
Tabs
Data Dictionary — every field defined and classified, with its quality rule.
Cleaning & Validation — every check run, its result, treatment, and business reason.
Timeline Reconciliation — the four departments' dates side by side and where they conflict.
Supplier Reliability — frequency and severity by supplier, plus active overdue exposure.
Launch Risk — launch SKUs mapped to supplier reliability, retail value, margin, and carton status.
Margin Economics — Austin actuals used to price a day of lost selling in a common unit.
Choice Set — three options priced in the same unit, with the recommendation.
Raw data tabs — Shipments, SKU Catalog, Austin Daily.
Cross-department sources used (Operations remains the acting function)
Finance: Denver lease summary terms; Austin store daily sales with COGS and gross margin.
HR: Denver applicant pipeline; Sales Associate offer letter; handbook training requirement.
These informed our timeline and margin math. Recommendations here are Operations decisions only.
Sample-size and coverage caveats
Song Hong's 12.1-day average rests on 12 completed orders; directional, not statistically tight.
No dataset provided contains a Denver store. Shipments, Austin sales, and customer data are all proxy
lanes, so Denver-specific behavior is inferred, not observed.
Austin is an established store; opening weeks typically run above its averages, so per-day margin here
is a conservative floor rather than a forecast.
Tools, Method & Verification
Analyzed in ChatGPT Work (reasoning tier) and Claude (Opus / Sonnet 4.6); independently recomputed in
Python/pandas; reproduced here as live Excel formulas so no figure rests on a number a model typed.
Validation: 0 duplicate POs, 0 required-field gaps, 0 date/status conflicts, 0 line-cost errors, 0
catalog-mapping errors, 0 Days_Late mismatches across 80 received rows.
Decision rights
Operations owns escalation and the exception-control call. Procurement owns spend and sourcing. Legal owns
contract terms. Store Manager confirms the required in-store date. AI calculates and flags; a human reviews
every trigger and makes the final decision.

## Data Dictionary
Data Dictionary
Field meanings confirmed before analysis. Classification separates inputs, calculated outcomes, and validation fields.
Dataset | Field | Business definition | Type | Classification | Quality rule
Shipments | PO_Number | Unique purchase-order identifier. | Text | Identifier | Required; unique; PO-#### format
Shipments | SKU | Stock-keeping unit identifier. | Text | Identifier | Required; maps to one catalog product
Shipments | Supplier | Vendor responsible for the shipment. | Text | Dimension | One spelling; maps to one country
Shipments | Promised_Date | Supplier-planned receipt date. | Date | Input | Must be >= order date
Shipments | Actual_Receipt_Date | Actual receipt; legitimately blank while in transit. | Date | Outcome | Required only when Received
Shipments | Status | Received or In transit. | Text | Status | Must agree with receipt-date presence
Shipments | Days_Late | Actual minus promised. Blank while in transit. | Number | Calculated outcome | Recalculate and match
Shipments | Line_Cost | Units multiplied by unit cost. | Currency | Calculated | Must reconcile
Derived | Current_Days_Overdue | Days past promise for an in-transit order as of As_of_Date. | Number | Calculated | Never replace unknown receipt with zero
Catalog | Lead_Time_Days | Planned supplier lead time. | Integer | Input | Order_By + Lead_Time implies in-store date
Catalog | Units_Per_Carton | Units in a full shipping carton. | Integer | Constraint | Launch buy should be a whole multiple
Catalog | Wholesale_Cost | Catalog cost per unit; merchandise only, excludes freight and duty. | Currency | Input | Must equal shipment unit cost
Catalog | Unit_Margin | MSRP minus wholesale cost; gross of landed freight and duty. | Currency | Calculated | Must reconcile
Austin (Finance) | COGS_USD | Cost of goods sold for the day. | Currency | Input | Used for realized margin rate
Austin (Finance) | Gross_Margin_USD | Net sales minus COGS. | Currency | Calculated | Basis for margin-per-day unit
Lease (Finance) | Delivery Date | Landlord tenant-ready delivery, on or about Sept 1 2026. | Date | External input | Soft date; no penalty for delay
Lease (Finance) | Build-out window | Customarily 6-8 weeks after delivery. | Range | External input | Drives earliest possible open
HR | Proposed_Start_Date | Offered start date by role. | Date | External input | Plus 2-week training = floor-ready date
HR | Offer_Accepted | Whether an extended offer was accepted. | Text | Outcome | Drives staffing coverage risk

## Cleaning & Validation
Cleaning & Validation
Issues documented transparently. Valid blanks preserved as unknowns; no source values silently changed.
# | Check | Result | Status | Treatment | Business reason
1 | Shipment row count | 96 rows present | Pass | Retained | Complete analysis population
2 | Duplicate PO numbers | 0 duplicates (PO-4400 to PO-4495) | Pass | No removal needed | Avoids double counting
3 | Required shipment fields | 0 missing required fields | Pass | No correction needed | Inputs complete
4 | Date logic (order <= promised) | 0 invalid sequences | Pass | No correction needed | Prevents negative lead-time errors
5 | Status / receipt consistency | 0 conflicts | Pass | No correction needed | Status controls eligible calculations
6 | Line-cost reconciliation | 0 mismatches | Pass | No correction needed | Protects cost totals
7 | Days_Late recalculation | 0 mismatches across 80 received rows | Pass | No correction needed | Verifies AI-reported delay math
8 | Cross-file catalog mapping | 0 mapping or economics mismatches | Pass | No correction needed | SKU, supplier, cost reconcile
9 | Valid in-transit blanks | 32 blanks across 16 rows | Expected | Preserved; measured against As_of_Date | An unknown receipt is not an on-time receipt
10 | Supplier name consistency | 4 suppliers, 1 spelling each in this file | Pass (watch) | Normalization retained in pipeline | An earlier export split one supplier across two spellings
11 | Launch carton multiples | 3 of 4 buys are not whole cartons (70.8, 66.7, 59.4) | Needs verification | Escalated for confirmation; source unchanged | Avoids receiving disputes at the dock
12 | 'On-time' definition | 0 early deliveries; 23 arrived exactly on promise | Documented | Report % late and avg days late together | On-time rate alone flatters suppliers never early
13 | Song Hong sample size | 12 completed orders | Documented | Treated as directional, not statistically tight | Prevents overstating a thin-sample average
14 | Denver coverage across datasets | 0 Denver records in shipments, Austin sales, or customer data | Documented | All Denver figures labeled as proxy-derived | Prevents presenting inference as observation
15 | Store name conflict (cross-dept) | HR applicant file says Denver-LoHi; lease and offer letter say Cherry Creek North | Open discrepancy | Flagged for confirmation; not resolved here | PO destination address must be right before shipping
16 | Required in-store date | Not stated in any Operations, Finance, or HR document reviewed | Open gap | Escalated to Store Manager | OPS-04 step 1 cannot be executed without it

## Timeline Reconciliation
Timeline Reconciliation — four departments, four dates
Every date below is read directly from a source document. The conflict is the finding.
Source | Department | What it establishes | Implied date | Status
SKU catalog: Order_By + Lead_Time | Operations | All four launch SKUs are planned to land on one date | October 12, 2026 | Planning assumption
Lease §3.1 Delivery | Finance/Legal | Landlord delivers tenant-ready 'on or about' Sept 1 | September 1, 2026 | Soft date, no penalty
Lease §3.4 Build-out | Finance/Legal | Build-out customarily requires 6-8 weeks after delivery | October 13 - 27, 2026 | Earliest open is Oct 13
Lease §4.2 Rent commencement | Finance/Legal | Rent starts on earlier of opening or 60 days after delivery | October 31, 2026 | Hard financial deadline
HR offer letters + handbook 3.3 | HR | Sales Associates start Sept 28; 2 weeks paid training required | October 12, 2026 | Zero slack; staffing incomplete
SH-2291 promise + Song Hong history | Operations | Oct 3 promise plus 12.1-day historical mean | ~October 15, 2026 | Planning inference
Required in-store date | Not found | OPS-04 step 1 requires it; no document states it | NOT ESTABLISHED | Open gap
The conflict: the earliest date the lease's own build-out window allows is October 13, one day after the October 12 date that Operations inventory planning, HR training, and the launch schedule are all built on. October 12 is not a tight date; it sits outside the lease's stated window. No document anywhere establishes a required in-store date, so the SOP's first planning step cannot be completed.

## Shipments Data
PO_Number | SKU | Product_Name | Supplier | Supplier_Country | Destination_Store | Order_Date | Promised_Date | Actual_Receipt_Date | Status | Days_Late | Units | Unit_Cost | Line_Cost
PO-4400 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Boise | 2026-02-11 | 2026-04-12 | 2026-04-20 | Received | 8 | 400 | 26 | 10400
PO-4401 | GT-JKT-08 | Recycled Denim Jacket | Andes Knitworks | Colombia | Spokane | 2025-12-16 | 2026-01-15 | 2026-01-15 | Received | 0 | 600 | 46 | 27600
PO-4402 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Portland-Division | 2026-05-20 | 2026-07-24 |  | In transit |  | 600 | 30 | 18000
PO-4403 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Tacoma | 2026-01-05 | 2026-03-11 | 2026-03-24 | Received | 13 | 200 | 30 | 6000
PO-4404 | GT-TNK-06 | Organic Tank Top | Delta Organics | India | Eugene | 2026-06-13 | 2026-07-28 |  | In transit |  | 250 | 11 | 2750
PO-4405 | GT-POL-05 | Performance Polo | Delta Organics | India | Tacoma | 2026-03-21 | 2026-05-05 | 2026-05-05 | Received | 0 | 150 | 19.5 | 2925
PO-4406 | GT-POL-05 | Performance Polo | Delta Organics | India | Spokane | 2026-04-18 | 2026-06-02 | 2026-06-02 | Received | 0 | 500 | 19.5 | 9750
PO-4407 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Seattle-Cap Hill | 2026-03-30 | 2026-06-03 | 2026-06-14 | Received | 11 | 250 | 30 | 7500
PO-4408 | GT-JKT-08 | Recycled Denim Jacket | Andes Knitworks | Colombia | Austin-South Congress | 2026-03-28 | 2026-04-27 | 2026-04-28 | Received | 1 | 500 | 46 | 23000
PO-4409 | GT-SHT-02 | Active Shorts | Mekong Textile Co. | Vietnam | Tacoma | 2026-05-27 | 2026-07-26 |  | In transit |  | 500 | 22 | 11000
PO-4410 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Salt Lake City | 2026-02-06 | 2026-04-12 | 2026-04-25 | Received | 13 | 250 | 30 | 7500
PO-4411 | GT-TNK-06 | Organic Tank Top | Delta Organics | India | Spokane | 2025-12-26 | 2026-02-09 | 2026-02-10 | Received | 1 | 600 | 11 | 6600
PO-4412 | GT-SHT-02 | Active Shorts | Mekong Textile Co. | Vietnam | Bend | 2026-03-20 | 2026-05-19 | 2026-05-31 | Received | 12 | 400 | 22 | 8800
PO-4413 | GT-POL-05 | Performance Polo | Delta Organics | India | Boulder | 2026-05-23 | 2026-07-07 | 2026-07-07 | Received | 0 | 400 | 19.5 | 7800
PO-4414 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Boise | 2026-02-10 | 2026-04-16 | 2026-04-27 | Received | 11 | 150 | 30 | 4500
PO-4415 | GT-SHT-02 | Active Shorts | Mekong Textile Co. | Vietnam | Boulder | 2026-04-10 | 2026-06-09 | 2026-06-15 | Received | 6 | 300 | 22 | 6600
PO-4416 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Tacoma | 2026-04-06 | 2026-06-05 | 2026-06-10 | Received | 5 | 250 | 26 | 6500
PO-4417 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Seattle-Ballard | 2025-12-16 | 2026-02-19 | 2026-02-26 | Received | 7 | 200 | 30 | 6000
PO-4418 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Seattle-Cap Hill | 2026-01-07 | 2026-03-13 | 2026-04-01 | Received | 19 | 600 | 30 | 18000
PO-4419 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Bend | 2026-06-14 | 2026-08-18 |  | In transit |  | 250 | 30 | 7500
PO-4420 | GT-HOD-04 | EcoFleece Hoodie | Andes Knitworks | Colombia | Boulder | 2026-03-21 | 2026-04-20 | 2026-04-20 | Received | 0 | 400 | 38 | 15200
PO-4421 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Seattle-Cap Hill | 2026-06-05 | 2026-08-04 |  | In transit |  | 400 | 26 | 10400
PO-4422 | GT-SHT-02 | Active Shorts | Mekong Textile Co. | Vietnam | Boise | 2026-04-30 | 2026-06-29 | 2026-07-04 | Received | 5 | 400 | 22 | 8800
PO-4423 | GT-HOD-04 | EcoFleece Hoodie | Andes Knitworks | Colombia | Boulder | 2025-12-27 | 2026-01-26 | 2026-01-26 | Received | 0 | 250 | 38 | 9500
PO-4424 | GT-JKT-08 | Recycled Denim Jacket | Andes Knitworks | Colombia | Spokane | 2026-02-12 | 2026-03-14 | 2026-03-15 | Received | 1 | 200 | 46 | 9200
PO-4425 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Bend | 2026-01-13 | 2026-03-14 | 2026-03-20 | Received | 6 | 200 | 26 | 5200
PO-4426 | GT-HOD-04 | EcoFleece Hoodie | Andes Knitworks | Colombia | Spokane | 2026-04-30 | 2026-05-30 | 2026-05-31 | Received | 1 | 150 | 38 | 5700
PO-4427 | GT-HOD-04 | EcoFleece Hoodie | Andes Knitworks | Colombia | Seattle-Cap Hill | 2026-03-10 | 2026-04-09 | 2026-04-10 | Received | 1 | 200 | 38 | 7600
PO-4428 | GT-HOD-04 | EcoFleece Hoodie | Andes Knitworks | Colombia | Tacoma | 2026-02-28 | 2026-03-30 | 2026-03-31 | Received | 1 | 250 | 38 | 9500
PO-4429 | GT-POL-05 | Performance Polo | Delta Organics | India | Portland-Pearl | 2026-05-28 | 2026-07-12 | 2026-07-14 | Received | 2 | 400 | 19.5 | 7800
PO-4430 | GT-JKT-08 | Recycled Denim Jacket | Andes Knitworks | Colombia | Seattle-Cap Hill | 2026-01-10 | 2026-02-09 | 2026-02-09 | Received | 0 | 300 | 46 | 13800
PO-4431 | GT-TEE-01 | Classic Tee | Delta Organics | India | Boise | 2026-05-19 | 2026-07-03 | 2026-07-04 | Received | 1 | 500 | 14.25 | 7125
PO-4432 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Portland-Division | 2026-03-06 | 2026-05-10 | 2026-05-27 | Received | 17 | 500 | 30 | 15000
PO-4433 | GT-SHT-02 | Active Shorts | Mekong Textile Co. | Vietnam | Austin-South Congress | 2026-05-25 | 2026-07-24 |  | In transit |  | 200 | 22 | 4400
PO-4434 | GT-HOD-04 | EcoFleece Hoodie | Andes Knitworks | Colombia | Eugene | 2026-02-04 | 2026-03-06 | 2026-03-06 | Received | 0 | 250 | 38 | 9500
PO-4435 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Eugene | 2026-02-01 | 2026-04-07 | 2026-04-18 | Received | 11 | 400 | 30 | 12000
PO-4436 | GT-POL-05 | Performance Polo | Delta Organics | India | Boise | 2026-02-04 | 2026-03-21 | 2026-03-21 | Received | 0 | 250 | 19.5 | 4875
PO-4437 | GT-TEE-01 | Classic Tee | Delta Organics | India | Austin-South Congress | 2026-02-26 | 2026-04-12 | 2026-04-12 | Received | 0 | 250 | 14.25 | 3562.5
PO-4438 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Spokane | 2026-03-21 | 2026-05-20 | 2026-06-01 | Received | 12 | 250 | 26 | 6500
PO-4439 | GT-HOD-04 | EcoFleece Hoodie | Andes Knitworks | Colombia | Portland-Pearl | 2026-03-15 | 2026-04-14 | 2026-04-14 | Received | 0 | 500 | 38 | 19000
PO-4440 | GT-POL-05 | Performance Polo | Delta Organics | India | Boise | 2026-02-08 | 2026-03-25 | 2026-03-26 | Received | 1 | 500 | 19.5 | 9750
PO-4441 | GT-JKT-08 | Recycled Denim Jacket | Andes Knitworks | Colombia | Portland-Pearl | 2026-04-17 | 2026-05-17 | 2026-05-18 | Received | 1 | 500 | 46 | 23000
PO-4442 | GT-TEE-01 | Classic Tee | Delta Organics | India | Spokane | 2026-01-31 | 2026-03-17 | 2026-03-18 | Received | 1 | 400 | 14.25 | 5700
PO-4443 | GT-JKT-08 | Recycled Denim Jacket | Andes Knitworks | Colombia | Seattle-Cap Hill | 2026-03-21 | 2026-04-20 | 2026-04-21 | Received | 1 | 500 | 46 | 23000
PO-4444 | GT-SHT-02 | Active Shorts | Mekong Textile Co. | Vietnam | Bend | 2026-05-25 | 2026-07-24 |  | In transit |  | 200 | 22 | 4400
PO-4445 | GT-POL-05 | Performance Polo | Delta Organics | India | Seattle-Ballard | 2026-05-26 | 2026-07-10 | 2026-07-10 | Received | 0 | 500 | 19.5 | 9750
PO-4446 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Bend | 2026-05-03 | 2026-07-02 | 2026-07-06 | Received | 4 | 250 | 26 | 6500
PO-4447 | GT-POL-05 | Performance Polo | Delta Organics | India | Spokane | 2026-04-26 | 2026-06-10 | 2026-06-10 | Received | 0 | 150 | 19.5 | 2925
PO-4448 | GT-SHT-02 | Active Shorts | Mekong Textile Co. | Vietnam | Eugene | 2026-05-31 | 2026-07-30 |  | In transit |  | 150 | 22 | 3300
PO-4449 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Bend | 2025-12-20 | 2026-02-23 | 2026-03-06 | Received | 11 | 150 | 30 | 4500
PO-4450 | GT-JKT-08 | Recycled Denim Jacket | Andes Knitworks | Colombia | Bend | 2026-06-05 | 2026-07-05 | 2026-07-05 | Received | 0 | 250 | 46 | 11500
PO-4451 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Tacoma | 2026-02-24 | 2026-04-30 | 2026-05-10 | Received | 10 | 600 | 30 | 18000
PO-4452 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Tacoma | 2025-12-29 | 2026-02-27 | 2026-03-03 | Received | 4 | 600 | 26 | 15600
PO-4453 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Bend | 2026-04-12 | 2026-06-11 | 2026-06-14 | Received | 3 | 500 | 26 | 13000
PO-4454 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Seattle-Cap Hill | 2026-03-17 | 2026-05-21 | 2026-06-01 | Received | 11 | 150 | 30 | 4500
PO-4455 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Seattle-Ballard | 2026-06-12 | 2026-08-11 |  | In transit |  | 500 | 26 | 13000
PO-4456 | GT-JKT-08 | Recycled Denim Jacket | Andes Knitworks | Colombia | Boise | 2026-03-06 | 2026-04-05 | 2026-04-05 | Received | 0 | 600 | 46 | 27600
PO-4457 | GT-TNK-06 | Organic Tank Top | Delta Organics | India | Spokane | 2026-06-02 | 2026-07-17 |  | In transit |  | 300 | 11 | 3300
PO-4458 | GT-HOD-04 | EcoFleece Hoodie | Andes Knitworks | Colombia | Austin-South Congress | 2026-06-13 | 2026-07-13 | 2026-07-14 | Received | 1 | 150 | 38 | 5700
PO-4459 | GT-JKT-08 | Recycled Denim Jacket | Andes Knitworks | Colombia | Austin-South Congress | 2025-12-20 | 2026-01-19 | 2026-01-20 | Received | 1 | 300 | 46 | 13800
PO-4460 | GT-POL-05 | Performance Polo | Delta Organics | India | Portland-Division | 2026-03-22 | 2026-05-06 | 2026-05-07 | Received | 1 | 250 | 19.5 | 4875
PO-4461 | GT-POL-05 | Performance Polo | Delta Organics | India | Austin-South Congress | 2026-05-28 | 2026-07-12 | 2026-07-12 | Received | 0 | 400 | 19.5 | 7800
PO-4462 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Boulder | 2026-06-02 | 2026-08-01 |  | In transit |  | 400 | 26 | 10400
PO-4463 | GT-SHT-02 | Active Shorts | Mekong Textile Co. | Vietnam | Seattle-Cap Hill | 2026-04-17 | 2026-06-16 | 2026-06-25 | Received | 9 | 150 | 22 | 3300
PO-4464 | GT-POL-05 | Performance Polo | Delta Organics | India | Tacoma | 2026-04-19 | 2026-06-03 | 2026-06-03 | Received | 0 | 400 | 19.5 | 7800
PO-4465 | GT-TNK-06 | Organic Tank Top | Delta Organics | India | Portland-Pearl | 2026-03-18 | 2026-05-02 | 2026-05-03 | Received | 1 | 150 | 11 | 1650
PO-4466 | GT-SHT-02 | Active Shorts | Mekong Textile Co. | Vietnam | Seattle-Cap Hill | 2026-03-29 | 2026-05-28 | 2026-06-02 | Received | 5 | 200 | 22 | 4400
PO-4467 | GT-TEE-01 | Classic Tee | Delta Organics | India | Seattle-Ballard | 2026-05-21 | 2026-07-05 | 2026-07-05 | Received | 0 | 200 | 14.25 | 2850
PO-4468 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Eugene | 2026-04-19 | 2026-06-18 | 2026-06-24 | Received | 6 | 150 | 26 | 3900
PO-4469 | GT-TNK-06 | Organic Tank Top | Delta Organics | India | Boulder | 2026-03-16 | 2026-04-30 | 2026-05-02 | Received | 2 | 300 | 11 | 3300
PO-4470 | GT-POL-05 | Performance Polo | Delta Organics | India | Tacoma | 2026-05-31 | 2026-07-15 |  | In transit |  | 500 | 19.5 | 9750
PO-4471 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Boise | 2026-05-13 | 2026-07-12 |  | In transit |  | 500 | 26 | 13000
PO-4472 | GT-TNK-06 | Organic Tank Top | Delta Organics | India | Salt Lake City | 2026-01-13 | 2026-02-27 | 2026-02-28 | Received | 1 | 600 | 11 | 6600
PO-4473 | GT-HOD-04 | EcoFleece Hoodie | Andes Knitworks | Colombia | Austin-South Congress | 2026-02-26 | 2026-03-28 | 2026-03-29 | Received | 1 | 500 | 38 | 19000
PO-4474 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Bend | 2026-04-01 | 2026-05-31 | 2026-06-11 | Received | 11 | 150 | 26 | 3900
PO-4475 | GT-TEE-01 | Classic Tee | Delta Organics | India | Spokane | 2026-05-24 | 2026-07-08 | 2026-07-09 | Received | 1 | 200 | 14.25 | 2850
PO-4476 | GT-TNK-06 | Organic Tank Top | Delta Organics | India | Seattle-Ballard | 2025-12-16 | 2026-01-30 | 2026-01-30 | Received | 0 | 150 | 11 | 1650
PO-4477 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Tacoma | 2025-12-22 | 2026-02-25 | 2026-03-08 | Received | 11 | 250 | 30 | 7500
PO-4478 | GT-HOD-04 | EcoFleece Hoodie | Andes Knitworks | Colombia | Portland-Division | 2026-02-16 | 2026-03-18 | 2026-03-18 | Received | 0 | 600 | 38 | 22800
PO-4479 | GT-SHT-02 | Active Shorts | Mekong Textile Co. | Vietnam | Bend | 2026-04-20 | 2026-06-19 | 2026-06-24 | Received | 5 | 600 | 22 | 13200
PO-4480 | GT-POL-05 | Performance Polo | Delta Organics | India | Seattle-Cap Hill | 2026-04-21 | 2026-06-05 | 2026-06-07 | Received | 2 | 200 | 19.5 | 3900
PO-4481 | GT-SHT-02 | Active Shorts | Mekong Textile Co. | Vietnam | Bend | 2026-03-08 | 2026-05-07 | 2026-05-14 | Received | 7 | 400 | 22 | 8800
PO-4482 | GT-POL-05 | Performance Polo | Delta Organics | India | Eugene | 2026-05-22 | 2026-07-06 | 2026-07-07 | Received | 1 | 250 | 19.5 | 4875
PO-4483 | GT-TEE-01 | Classic Tee | Delta Organics | India | Salt Lake City | 2026-06-01 | 2026-07-16 |  | In transit |  | 150 | 14.25 | 2137.5
PO-4484 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Bend | 2025-12-18 | 2026-02-16 | 2026-02-26 | Received | 10 | 600 | 26 | 15600
PO-4485 | GT-TNK-06 | Organic Tank Top | Delta Organics | India | Austin-South Congress | 2026-02-19 | 2026-04-05 | 2026-04-07 | Received | 2 | 250 | 11 | 2750
PO-4486 | GT-CHN-07 | Slim Chino | Mekong Textile Co. | Vietnam | Bend | 2026-06-11 | 2026-08-10 |  | In transit |  | 150 | 26 | 3900
PO-4487 | GT-POL-05 | Performance Polo | Delta Organics | India | Austin-South Congress | 2025-12-25 | 2026-02-08 | 2026-02-09 | Received | 1 | 600 | 19.5 | 11700
PO-4488 | GT-JKT-08 | Recycled Denim Jacket | Andes Knitworks | Colombia | Tacoma | 2025-12-23 | 2026-01-22 | 2026-01-22 | Received | 0 | 150 | 46 | 6900
PO-4489 | GT-TEE-01 | Classic Tee | Delta Organics | India | Tacoma | 2025-12-29 | 2026-02-12 | 2026-02-14 | Received | 2 | 300 | 14.25 | 4275
PO-4490 | GT-TNK-06 | Organic Tank Top | Delta Organics | India | Austin-South Congress | 2026-04-06 | 2026-05-21 | 2026-05-21 | Received | 0 | 300 | 11 | 3300
PO-4491 | GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | Vietnam | Austin-South Congress | 2026-05-08 | 2026-07-12 |  | In transit |  | 500 | 30 | 15000
PO-4492 | GT-JKT-08 | Recycled Denim Jacket | Andes Knitworks | Colombia | Portland-Division | 2025-12-30 | 2026-01-29 | 2026-01-30 | Received | 1 | 600 | 46 | 27600
PO-4493 | GT-TEE-01 | Classic Tee | Delta Organics | India | Portland-Division | 2026-01-06 | 2026-02-20 | 2026-02-21 | Received | 1 | 200 | 14.25 | 2850
PO-4494 | GT-JKT-08 | Recycled Denim Jacket | Andes Knitworks | Colombia | Bend | 2026-04-13 | 2026-05-13 | 2026-05-14 | Received | 1 | 500 | 46 | 23000
PO-4495 | GT-HOD-04 | EcoFleece Hoodie | Andes Knitworks | Colombia | Bend | 2026-04-18 | 2026-05-18 | 2026-05-18 | Received | 0 | 500 | 38 | 19000

## SKU Catalog
SKU | Product_Name | Category | Material | Sustainability_Cert | Supplier | Supplier_Country | Lead_Time_Days | MOQ_Units | Wholesale_Cost | MSRP | Unit_Margin | Margin_Pct | Units_Per_Carton | In_Denver_Launch | Denver_Opening_Buy_Units | Opening_Buy_Cost | Opening_Buy_Retail_Value | Order_By_Date | Days_Until_Order_Deadline | Notes
GT-HOD-04 | EcoFleece Hoodie | Outerwear | Recycled fleece | GRS | Andes Knitworks | Colombia | 30 | 200 | 38 | 98 | 60 | 0.612 | 12 | Y | 850 | 32300 | 83300 | 2026-09-12 | 60
GT-JKT-08 | Recycled Denim Jacket | Outerwear | Recycled denim | GRS | Andes Knitworks | Colombia | 35 | 150 | 46 | 118 | 72 | 0.61 | 8 | N | 0 | 0 | 0 |  |  | In GreenThreads catalog; stocked at other stores. Not in the Denver launch assortment.
GT-TEE-01 | Classic Tee | Tops | Organic cotton | GOTS | Delta Organics | India | 45 | 500 | 14.25 | 38 | 23.75 | 0.625 | 24 | Y | 1600 | 22800 | 60800 | 2026-08-28 | 45
GT-POL-05 | Performance Polo | Tops | Recycled pique | GRS | Delta Organics | India | 45 | 400 | 19.5 | 52 | 32.5 | 0.625 | 24 | N | 0 | 0 | 0 |  |  | In GreenThreads catalog; stocked at other stores. Not in the Denver launch assortment.
GT-TNK-06 | Organic Tank Top | Tops | Organic cotton | GOTS | Delta Organics | India | 40 | 500 | 11 | 30 | 19 | 0.633 | 30 | N | 0 | 0 | 0 |  |  | In GreenThreads catalog; stocked at other stores. Not in the Denver launch assortment.
GT-SHT-02 | Active Shorts | Bottoms | Recycled polyester | GRS | Mekong Textile Co. | Vietnam | 60 | 300 | 22 | 58 | 36 | 0.621 | 20 | Y | 1200 | 26400 | 69600 | 2026-08-13 | 30
GT-CHN-07 | Slim Chino | Bottoms | Hemp-cotton blend | OEKO-TEX | Mekong Textile Co. | Vietnam | 60 | 300 | 26 | 68 | 42 | 0.618 | 20 | N | 0 | 0 | 0 |  |  | In GreenThreads catalog; stocked at other stores. Not in the Denver launch assortment.
GT-JOG-03 | Bamboo Joggers | Bottoms | Bamboo viscose | OEKO-TEX | Song Hong Apparel | Vietnam | 65 | 250 | 30 | 78 | 48 | 0.615 | 16 | Y | 950 | 28500 | 74100 | 2026-08-08 | 25

## Austin Daily
Date | Store | Day_Of_Week | Foot_Traffic | Transactions | Units_Sold | Gross_Sales_USD | Returns_USD | Net_Sales_USD | COGS_USD | Gross_Margin_USD | Avg_Transaction_USD
2026-03-02 | Austin-South Congress | Mon | 362 | 74 | 115 | 6764.33 | 275.48 | 6488.85 | 2540.89 | 3947.96 | 87.69
2026-03-03 | Austin-South Congress | Tue | 385 | 72 | 87 | 7141.2 | 314.08 | 6827.12 | 2695.9 | 4131.22 | 94.82
2026-03-04 | Austin-South Congress | Wed | 403 | 86 | 131 | 6367.06 | 395.03 | 5972.03 | 2298.73 | 3673.3 | 69.44
2026-03-05 | Austin-South Congress | Thu | 431 | 90 | 137 | 7548.79 | 449.85 | 7098.94 | 2793.69 | 4305.25 | 78.88
2026-03-06 | Austin-South Congress | Fri | 464 | 99 | 174 | 9481.01 | 550.4 | 8930.61 | 3435.95 | 5494.66 | 90.21
2026-03-07 | Austin-South Congress | Sat | 687 | 144 | 211 | 12312.62 | 811.84 | 11500.78 | 4432.6 | 7068.18 | 79.87
2026-03-08 | Austin-South Congress | Sun | 314 | 87 | 105 | 8414.76 | 188.94 | 8225.82 | 3230.85 | 4994.97 | 94.55
2026-03-09 | Austin-South Congress | Mon | 294 | 60 | 76 | 5774.19 | 378.95 | 5395.24 | 2063.1 | 3332.14 | 89.92
2026-03-10 | Austin-South Congress | Tue | 227 | 57 | 70 | 6354.09 | 157.61 | 6196.48 | 2421.09 | 3775.39 | 108.71
2026-03-11 | Austin-South Congress | Wed | 293 | 76 | 109 | 5998.99 | 297.18 | 5701.81 | 2184.14 | 3517.67 | 75.02
2026-03-12 | Austin-South Congress | Thu | 204 | 61 | 98 | 7587.88 | 165.75 | 7422.13 | 2927.56 | 4494.57 | 121.67
2026-03-13 | Austin-South Congress | Fri | 372 | 85 | 149 | 8028.81 | 355.65 | 7673.16 | 2961.35 | 4711.81 | 90.27
2026-03-14 | Austin-South Congress | Sat | 717 | 140 | 281 | 10007.58 | 363.82 | 9643.76 | 3769.26 | 5874.5 | 68.88
2026-03-15 | Austin-South Congress | Sun | 360 | 92 | 163 | 7213.46 | 389.91 | 6823.55 | 2667.56 | 4155.99 | 74.17
2026-03-16 | Austin-South Congress | Mon | 232 | 48 | 62 | 5171.46 | 284.35 | 4887.11 | 1878.59 | 3008.52 | 101.81
2026-03-17 | Austin-South Congress | Tue | 360 | 80 | 130 | 5639.82 | 320.77 | 5319.05 | 2052.12 | 3266.93 | 66.49
2026-03-18 | Austin-South Congress | Wed | 275 | 53 | 109 | 6102.38 | 185.71 | 5916.67 | 2242.53 | 3674.14 | 111.64
2026-03-19 | Austin-South Congress | Thu | 320 | 69 | 116 | 5881.17 | 278.29 | 5602.88 | 2192.65 | 3410.23 | 81.2
2026-03-20 | Austin-South Congress | Fri | 389 | 87 | 177 | 7776.87 | 437.27 | 7339.6 | 2864.9 | 4474.7 | 84.36
2026-03-21 | Austin-South Congress | Sat | 423 | 108 | 194 | 9330.19 | 223.4 | 9106.79 | 3565.35 | 5541.44 | 84.32
2026-03-22 | Austin-South Congress | Sun | 286 | 70 | 98 | 6502.47 | 208.47 | 6294 | 2422.35 | 3871.65 | 89.91
2026-03-23 | Austin-South Congress | Mon | 220 | 40 | 80 | 5296.62 | 363.93 | 4932.69 | 1944.4 | 2988.29 | 123.32
2026-03-24 | Austin-South Congress | Tue | 365 | 68 | 115 | 4993.63 | 201.56 | 4792.07 | 1831.22 | 2960.85 | 70.47
2026-03-25 | Austin-South Congress | Wed | 214 | 46 | 59 | 5057.33 | 112.72 | 4944.61 | 1869.77 | 3074.84 | 107.49
2026-03-26 | Austin-South Congress | Thu | 278 | 57 | 86 | 5813.1 | 290.06 | 5523.04 | 2088.66 | 3434.38 | 96.9
2026-03-27 | Austin-South Congress | Fri | 325 | 89 | 138 | 7311.71 | 161.82 | 7149.89 | 2775.4 | 4374.49 | 80.34
2026-03-28 | Austin-South Congress | Sat | 468 | 103 | 188 | 9231.16 | 192.69 | 9038.47 | 3407.99 | 5630.48 | 87.75
2026-03-29 | Austin-South Congress | Sun | 269 | 61 | 90 | 6176.63 | 304.79 | 5871.84 | 2315.74 | 3556.1 | 96.26
2026-03-30 | Austin-South Congress | Mon | 196 | 41 | 70 | 4973.88 | 305.29 | 4668.59 | 1799.82 | 2868.77 | 113.87
2026-03-31 | Austin-South Congress | Tue | 220 | 55 | 74 | 5077.15 | 251.37 | 4825.78 | 1851.7 | 2974.08 | 87.74
2026-04-01 | Austin-South Congress | Wed | 203 | 55 | 95 | 4732.43 | 110.96 | 4621.47 | 1811.94 | 2809.53 | 84.03
2026-04-02 | Austin-South Congress | Thu | 289 | 63 | 93 | 5722.14 | 270.19 | 5451.95 | 2117.65 | 3334.3 | 86.54
2026-04-03 | Austin-South Congress | Fri | 287 | 82 | 123 | 6515.19 | 164.04 | 6351.15 | 2496.73 | 3854.42 | 77.45
2026-04-04 | Austin-South Congress | Sat | 416 | 90 | 187 | 8008.76 | 161.39 | 7847.37 | 3083.74 | 4763.63 | 87.19
2026-04-05 | Austin-South Congress | Sun | 241 | 71 | 111 | 6712.25 | 411.98 | 6300.27 | 2417 | 3883.27 | 88.74
2026-04-06 | Austin-South Congress | Mon | 261 | 58 | 86 | 4497.19 | 308.35 | 4188.84 | 1626.66 | 2562.18 | 72.22
2026-04-07 | Austin-South Congress | Tue | 147 | 42 | 52 | 4032.93 | 107.84 | 3925.09 | 1497.93 | 2427.16 | 93.45
2026-04-08 | Austin-South Congress | Wed | 259 | 54 | 98 | 4480.8 | 191.2 | 4289.6 | 1663.31 | 2626.29 | 79.44
2026-04-09 | Austin-South Congress | Thu | 302 | 58 | 121 | 4943.72 | 187.22 | 4756.5 | 1866.58 | 2889.92 | 82.01
2026-04-10 | Austin-South Congress | Fri | 262 | 76 | 119 | 7339.39 | 228.79 | 7110.6 | 2748.25 | 4362.35 | 93.56
2026-04-11 | Austin-South Congress | Sat | 436 | 98 | 145 | 8609.53 | 508.37 | 8101.16 | 3096.52 | 5004.64 | 82.66
2026-04-12 | Austin-South Congress | Sun | 306 | 68 | 121 | 6073.45 | 127.43 | 5946.02 | 2318.89 | 3627.13 | 87.44
2026-04-13 | Austin-South Congress | Mon | 210 | 42 | 52 | 4479.26 | 210.69 | 4268.57 | 1647.38 | 2621.19 | 101.63
2026-04-14 | Austin-South Congress | Tue | 193 | 38 | 70 | 4305.85 | 103.58 | 4202.27 | 1594.2 | 2608.07 | 110.59
2026-04-15 | Austin-South Congress | Wed | 150 | 44 | 71 | 4913.95 | 342.85 | 4571.1 | 1760.8 | 2810.3 | 103.89
2026-04-16 | Austin-South Congress | Thu | 340 | 71 | 102 | 4973.94 | 206.87 | 4767.07 | 1880.54 | 2886.53 | 67.14
2026-04-17 | Austin-South Congress | Fri | 295 | 61 | 78 | 6450.88 | 407.04 | 6043.84 | 2266.67 | 3777.17 | 99.08
2026-04-18 | Austin-South Congress | Sat | 339 | 70 | 141 | 7445.74 | 413.11 | 7032.63 | 2751.69 | 4280.94 | 100.47
2026-04-19 | Austin-South Congress | Sun | 247 | 46 | 82 | 5251.95 | 340.29 | 4911.66 | 1868.07 | 3043.59 | 106.78
2026-04-20 | Austin-South Congress | Mon | 286 | 59 | 118 | 4074.98 | 138.68 | 3936.3 | 1512.18 | 2424.12 | 66.72
2026-04-21 | Austin-South Congress | Tue | 205 | 41 | 74 | 4514.35 | 301.87 | 4212.48 | 1651.58 | 2560.9 | 102.74
2026-04-22 | Austin-South Congress | Wed | 227 | 61 | 112 | 4384.4 | 156.47 | 4227.93 | 1589.54 | 2638.39 | 69.31
2026-04-23 | Austin-South Congress | Thu | 287 | 53 | 76 | 5194.01 | 229.36 | 4964.65 | 1954.05 | 3010.6 | 93.67
2026-04-24 | Austin-South Congress | Fri | 389 | 89 | 159 | 6644.8 | 455.87 | 6188.93 | 2372.57 | 3816.36 | 69.54
2026-04-25 | Austin-South Congress | Sat | 307 | 72 | 111 | 7311.66 | 502.38 | 6809.28 | 2553.85 | 4255.43 | 94.57
2026-04-26 | Austin-South Congress | Sun | 230 | 69 | 132 | 5865.72 | 232.95 | 5632.77 | 2123.55 | 3509.22 | 81.63
2026-04-27 | Austin-South Congress | Mon | 134 | 35 | 66 | 3651.3 | 127.12 | 3524.18 | 1333.23 | 2190.95 | 100.69
2026-04-28 | Austin-South Congress | Tue | 178 | 34 | 43 | 3960.59 | 163.23 | 3797.36 | 1482.54 | 2314.82 | 111.69
2026-04-29 | Austin-South Congress | Wed | 263 | 54 | 100 | 4070.19 | 195.97 | 3874.22 | 1459.32 | 2414.9 | 71.74
2026-04-30 | Austin-South Congress | Thu | 172 | 41 | 82 | 5070.54 | 248.42 | 4822.12 | 1903.05 | 2919.07 | 117.61
2026-05-01 | Austin-South Congress | Fri | 208 | 46 | 95 | 4988.31 | 245.93 | 4742.38 | 1847.26 | 2895.12 | 103.1
2026-05-02 | Austin-South Congress | Sat | 206 | 60 | 102 | 6766.32 | 304.74 | 6461.58 | 2509.57 | 3952.01 | 107.69
2026-05-03 | Austin-South Congress | Sun | 280 | 51 | 63 | 5010.88 | 173.27 | 4837.61 | 1850.85 | 2986.76 | 94.86
2026-05-04 | Austin-South Congress | Mon | 120 | 30 | 57 | 3186.62 | 181.41 | 3005.21 | 1156.37 | 1848.84 | 100.17
2026-05-05 | Austin-South Congress | Tue | 133 | 32 | 62 | 3448.4 | 237.47 | 3210.93 | 1229.58 | 1981.35 | 100.34
2026-05-06 | Austin-South Congress | Wed | 173 | 50 | 82 | 4047.85 | 87.55 | 3960.3 | 1552.7 | 2407.6 | 79.21
2026-05-07 | Austin-South Congress | Thu | 193 | 37 | 47 | 4465 | 179.47 | 4285.53 | 1655.94 | 2629.59 | 115.83
2026-05-08 | Austin-South Congress | Fri | 235 | 50 | 72 | 5663.78 | 192.12 | 5471.66 | 2052.66 | 3419 | 109.43
2026-05-09 | Austin-South Congress | Sat | 279 | 56 | 104 | 5767.9 | 127.74 | 5640.16 | 2146.84 | 3493.32 | 100.72
2026-05-10 | Austin-South Congress | Sun | 234 | 52 | 86 | 4776.04 | 224.97 | 4551.07 | 1784.76 | 2766.31 | 87.52
2026-05-11 | Austin-South Congress | Mon | 133 | 32 | 66 | 3236.66 | 78.07 | 3158.59 | 1231.44 | 1927.15 | 98.71
2026-05-12 | Austin-South Congress | Tue | 168 | 39 | 76 | 3157.75 | 68.75 | 3089 | 1171.37 | 1917.63 | 79.21
2026-05-13 | Austin-South Congress | Wed | 198 | 51 | 82 | 4057.8 | 241.63 | 3816.17 | 1460.63 | 2355.54 | 74.83
2026-05-14 | Austin-South Congress | Thu | 252 | 62 | 128 | 4196.33 | 271.45 | 3924.88 | 1511.05 | 2413.83 | 63.3
2026-05-15 | Austin-South Congress | Fri | 199 | 45 | 57 | 4826.91 | 180.2 | 4646.71 | 1743.15 | 2903.56 | 103.26
2026-05-16 | Austin-South Congress | Sat | 333 | 75 | 131 | 6257.11 | 375.75 | 5881.36 | 2280.89 | 3600.47 | 78.42
2026-05-17 | Austin-South Congress | Sun | 266 | 63 | 128 | 4341.11 | 163.17 | 4177.94 | 1645.77 | 2532.17 | 66.32
2026-05-18 | Austin-South Congress | Mon | 150 | 37 | 74 | 3665.3 | 113.12 | 3552.18 | 1395.55 | 2156.63 | 96
2026-05-19 | Austin-South Congress | Tue | 236 | 43 | 64 | 3501.54 | 193.15 | 3308.39 | 1248.9 | 2059.49 | 76.94
2026-05-20 | Austin-South Congress | Wed | 202 | 37 | 62 | 3334.79 | 94.04 | 3240.75 | 1243.47 | 1997.28 | 87.59
2026-05-21 | Austin-South Congress | Thu | 182 | 43 | 80 | 4057.91 | 214.23 | 3843.68 | 1469.07 | 2374.61 | 89.39
2026-05-22 | Austin-South Congress | Fri | 204 | 44 | 53 | 5285.23 | 306.24 | 4978.99 | 1900.42 | 3078.57 | 113.16
2026-05-23 | Austin-South Congress | Sat | 220 | 58 | 90 | 6375.76 | 311.61 | 6064.15 | 2311.99 | 3752.16 | 104.55
2026-05-24 | Austin-South Congress | Sun | 150 | 43 | 75 | 4552.33 | 277.65 | 4274.68 | 1670.14 | 2604.54 | 99.41
2026-05-25 | Austin-South Congress | Mon | 100 | 30 | 41 | 3467.36 | 165.57 | 3301.79 | 1268.39 | 2033.4 | 110.06
2026-05-26 | Austin-South Congress | Tue | 160 | 29 | 56 | 3713.23 | 221.32 | 3491.91 | 1347.5 | 2144.41 | 120.41
2026-05-27 | Austin-South Congress | Wed | 186 | 35 | 51 | 3468.83 | 83.58 | 3385.25 | 1320.17 | 2065.08 | 96.72
2026-05-28 | Austin-South Congress | Thu | 248 | 55 | 69 | 4466.52 | 194.98 | 4271.54 | 1664.23 | 2607.31 | 77.66
2026-05-29 | Austin-South Congress | Fri | 220 | 48 | 81 | 4809.17 | 328.2 | 4480.97 | 1717.36 | 2763.61 | 93.35
2026-05-30 | Austin-South Congress | Sat | 276 | 73 | 142 | 6000.04 | 233.13 | 5766.91 | 2266.25 | 3500.66 | 79
2026-05-31 | Austin-South Congress | Sun | 146 | 43 | 70 | 4334.92 | 127.75 | 4207.17 | 1589.93 | 2617.24 | 97.84
2026-06-01 | Austin-South Congress | Mon | 122 | 36 | 64 | 3214.79 | 206.15 | 3008.64 | 1130.52 | 1878.12 | 83.57
2026-06-02 | Austin-South Congress | Tue | 126 | 35 | 42 | 3652.69 | 203.68 | 3449.01 | 1297.38 | 2151.63 | 98.54
2026-06-03 | Austin-South Congress | Wed | 155 | 41 | 65 | 3525.99 | 126.51 | 3399.48 | 1315.35 | 2084.13 | 82.91
2026-06-04 | Austin-South Congress | Thu | 263 | 57 | 119 | 3924.23 | 121.28 | 3802.95 | 1472.47 | 2330.48 | 66.72
2026-06-05 | Austin-South Congress | Fri | 177 | 52 | 92 | 4858.09 | 141.4 | 4716.69 | 1859.18 | 2857.51 | 90.71
2026-06-06 | Austin-South Congress | Sat | 262 | 73 | 117 | 5938.43 | 324.33 | 5614.1 | 2178.06 | 3436.04 | 76.91
2026-06-07 | Austin-South Congress | Sun | 124 | 34 | 68 | 4321.59 | 254.67 | 4066.92 | 1555.87 | 2511.05 | 119.62
2026-06-08 | Austin-South Congress | Mon | 110 | 33 | 41 | 3359.56 | 104.17 | 3255.39 | 1232.7 | 2022.69 | 98.65
2026-06-09 | Austin-South Congress | Tue | 225 | 44 | 83 | 3257.1 | 83.46 | 3173.64 | 1226.11 | 1947.53 | 72.13
2026-06-10 | Austin-South Congress | Wed | 136 | 39 | 76 | 3674.07 | 74.45 | 3599.62 | 1374.12 | 2225.5 | 92.3
2026-06-11 | Austin-South Congress | Thu | 162 | 39 | 81 | 4033.59 | 122.56 | 3911.03 | 1543.49 | 2367.54 | 100.28
2026-06-12 | Austin-South Congress | Fri | 221 | 54 | 74 | 5017.83 | 283.16 | 4734.67 | 1803.68 | 2930.99 | 87.68
2026-06-13 | Austin-South Congress | Sat | 256 | 70 | 84 | 6816.19 | 335.39 | 6480.8 | 2532.88 | 3947.92 | 92.58
2026-06-14 | Austin-South Congress | Sun | 153 | 46 | 62 | 4315.32 | 141.98 | 4173.34 | 1574.23 | 2599.11 | 90.72
2026-06-15 | Austin-South Congress | Mon | 131 | 36 | 74 | 3026.38 | 124.25 | 2902.13 | 1088.89 | 1813.24 | 80.61
2026-06-16 | Austin-South Congress | Tue | 281 | 52 | 83 | 3528.72 | 87.38 | 3441.34 | 1317.98 | 2123.36 | 66.18
2026-06-17 | Austin-South Congress | Wed | 127 | 31 | 49 | 3448.89 | 230.94 | 3217.95 | 1207.79 | 2010.16 | 103.8
2026-06-18 | Austin-South Congress | Thu | 105 | 31 | 58 | 4176.91 | 246.41 | 3930.5 | 1483.29 | 2447.21 | 126.79
2026-06-19 | Austin-South Congress | Fri | 148 | 42 | 79 | 4928.16 | 147.42 | 4780.74 | 1833.59 | 2947.15 | 113.83
2026-06-20 | Austin-South Congress | Sat | 325 | 63 | 126 | 6131.37 | 386.39 | 5744.98 | 2159.35 | 3585.63 | 91.19
2026-06-21 | Austin-South Congress | Sun | 180 | 41 | 56 | 4377.8 | 260.19 | 4117.61 | 1598.81 | 2518.8 | 100.43
2026-06-22 | Austin-South Congress | Mon | 127 | 32 | 58 | 3131.88 | 208.09 | 2923.79 | 1154.06 | 1769.73 | 91.37
2026-06-23 | Austin-South Congress | Tue | 118 | 31 | 51 | 3679.83 | 95.12 | 3584.71 | 1407.73 | 2176.98 | 115.64
2026-06-24 | Austin-South Congress | Wed | 168 | 36 | 68 | 3925.57 | 115.72 | 3809.85 | 1470.87 | 2338.98 | 105.83
2026-06-25 | Austin-South Congress | Thu | 209 | 38 | 70 | 3874.34 | 250.73 | 3623.61 | 1416.25 | 2207.36 | 95.36
2026-06-26 | Austin-South Congress | Fri | 190 | 55 | 110 | 5395.14 | 343.01 | 5052.13 | 1974.48 | 3077.65 | 91.86
2026-06-27 | Austin-South Congress | Sat | 367 | 68 | 100 | 6633.08 | 414.13 | 6218.95 | 2404.7 | 3814.25 | 91.46
2026-06-28 | Austin-South Congress | Sun | 179 | 52 | 79 | 5048.24 | 187.5 | 4860.74 | 1839.92 | 3020.82 | 93.48
2026-06-29 | Austin-South Congress | Mon | 153 | 28 | 38 | 3467.41 | 126.24 | 3341.17 | 1305.56 | 2035.61 | 119.33
2026-06-30 | Austin-South Congress | Tue | 157 | 31 | 38 | 3216.85 | 87.25 | 3129.6 | 1231.33 | 1898.27 | 100.95
2026-07-01 | Austin-South Congress | Wed | 231 | 45 | 79 | 3980.51 | 81.06 | 3899.45 | 1502.34 | 2397.11 | 86.65
2026-07-02 | Austin-South Congress | Thu | 279 | 54 | 98 | 4442.69 | 177.34 | 4265.35 | 1672.58 | 2592.77 | 78.99
2026-07-03 | Austin-South Congress | Fri | 174 | 39 | 80 | 5096.65 | 199.62 | 4897.03 | 1873.43 | 3023.6 | 125.56
2026-07-04 | Austin-South Congress | Sat | 279 | 61 | 117 | 5832.32 | 243.08 | 5589.24 | 2200.38 | 3388.86 | 91.63
2026-07-05 | Austin-South Congress | Sun | 246 | 57 | 68 | 5018.37 | 148.57 | 4869.8 | 1847.23 | 3022.57 | 85.44
2026-07-06 | Austin-South Congress | Mon | 152 | 34 | 54 | 3556.51 | 227.58 | 3328.93 | 1301.65 | 2027.28 | 97.91
2026-07-07 | Austin-South Congress | Tue | 107 | 29 | 56 | 3164.74 | 144.93 | 3019.81 | 1156.85 | 1862.96 | 104.13
2026-07-08 | Austin-South Congress | Wed | 227 | 66 | 85 | 3967.56 | 87.81 | 3879.75 | 1459.06 | 2420.69 | 58.78
2026-07-09 | Austin-South Congress | Thu | 201 | 40 | 71 | 4073.36 | 252.03 | 3821.33 | 1508.31 | 2313.02 | 95.53
2026-07-10 | Austin-South Congress | Fri | 349 | 81 | 102 | 5739.43 | 167.78 | 5571.65 | 2120.99 | 3450.66 | 68.79
2026-07-11 | Austin-South Congress | Sat | 351 | 67 | 101 | 6012.79 | 342.04 | 5670.75 | 2221.2 | 3449.55 | 84.64
2026-07-12 | Austin-South Congress | Sun | 349 | 69 | 91 | 4988.02 | 329.22 | 4658.8 | 1751.51 | 2907.29 | 67.52
2026-07-13 | Austin-South Congress | Mon | 164 | 34 | 64 | 3621.24 | 216.24 | 3405 | 1340.97 | 2064.03 | 100.15

## Supplier Reliability
Supplier Reliability — frequency, severity, active exposure
Frequency and severity both reported; they answer different questions. Tier flags severity above 3 days.
As_of_Date: |  | 2026-08-18
Supplier | Country | Received | Late (>0d) | % Late | Avg Days Late | Max | In Transit | Overdue Now | Tier
Song Hong Apparel | Vietnam | 12 | 12 | 100% | 12.0833 | 19 | 3 | 2 | At risk
Mekong Textile Co. | Vietnam | 17 | 17 | 100% | 6.9412 | 12 | 9 | 9 | At risk
Delta Organics | India | 28 | 16 | 57.14% | 0.75 | 2 | 4 | 4 | Reliable
Andes Knitworks | Colombia | 23 | 12 | 52.17% | 0.52174 | 1 | 0 | 0 | Reliable
Both Vietnam suppliers are late on 100% of completed orders. Song Hong's average rests on 12 orders and is directional.

## Margin Economics
Margin Economics — pricing a day of lost selling
Austin store actuals (134 days) give a company-sourced margin rate, replacing the estimated sell-through used previously.
Metric | Value | Source / formula
Days of Austin data | 134 | Austin Daily, Mar 2 - Jul 13 2026
Total net sales | 668763.15 | Sum of Net_Sales_USD
Total COGS | 258167.21 | Sum of COGS_USD
Total gross margin | 410595.94 | Sum of Gross_Margin_USD
Realized gross margin % | 61.4% | Gross margin divided by net sales
Catalog theoretical margin % | 0.620 | Catalog Margin_Pct average; realized rate closely tracks it
Avg units sold per day | 92.7537 | Average of Units_Sold
Avg gross margin per day | 3064.1488 | Average of Gross_Margin_USD
Gross margin per unit sold | 33.0353 | Total margin divided by total units
Saturday avg gross margin | 4333.69 | Peak-day rate; opening days run above average
Common unit for the choice set: one day of lost selling at the Austin rate is roughly one average day of gross margin. Austin is an established store, so this is a conservative floor for an opening week, not a forecast.

## Launch Risk
Denver Launch Risk
Launch SKUs mapped to supplier severity, with retail value and margin exposure and carton status.
SKU | Product | Supplier | Units | Retail Value | Unit Margin | Launch Margin | Avg Days Late | Units/Carton | Cartons | Tier | Margin at Risk
GT-HOD-04 | EcoFleece Hoodie | Andes Knitworks | 850 | 83300 | 60 | 51000 | 0.52174 | 12 | Partial | Reliable | 0
GT-TEE-01 | Classic Tee | Delta Organics | 1600 | 60800 | 23.75 | 38000 | 0.75 | 24 | Partial | Reliable | 0
GT-SHT-02 | Active Shorts | Mekong Textile Co. | 1200 | 69600 | 36 | 43200 | 6.9412 | 20 | Whole | At risk | 43200
GT-JOG-03 | Bamboo Joggers | Song Hong Apparel | 950 | 74100 | 48 | 45600 | 12.0833 | 16 | Partial | At risk | 45600
|  | TOTAL | 4600 | 287800 |  | 177800 |  |  |  |  | 88800
Retail value at risk: |  |  |  | 143700 |  | 88800

## Choice Set
Choice Set & Recommendation
Assumptions (yellow = estimate or judgment, not measured)
Common unit | Days of selling protected, valued at the Austin realized gross-margin rate
Earliest possible open | October 13, 2026 — lease delivery Sept 1 plus the 6-week end of the stated build-out window
Rent clock | Begins October 31 regardless of whether the store has opened (lease §4.2)
Supplier slip | Song Hong ~12 days, Mekong ~7 days, from their own completed-order history
Freight and duty | Wholesale cost is merchandise only; landed COGS is higher, so margin shown is gross of both
Expedite cost | Quote-based; no freight figure is invented in this analysis
Options
Option | Operating move | Priced in the common unit | Trade-off / limitation | Position
A. Hold to Oct 12 | Keep the current plan and promised dates; assume the store is ready. | Protects 0 days. If build-out runs past Oct 12, inventory arrives into a store that cannot open and the full at-risk margin stays exposed. | No cost today, but plans against a date outside the lease's own window. | Reject
B. Control | Confirm the required in-store date with the Store Manager, require ex-factory, container-load, booking and weekly milestones on both Vietnam POs, and test the SOP two-week buffer. | Protects the ability to act; buys roughly 2 weeks of decision time at no freight cost. | Visibility alone creates no backup if a milestone slips. | Partial
C. Gate (recommended) | Adopt B, re-baseline the plan to the confirmed date, secure partial-expedite and backup-source quotes now, and release spend only on a verified trigger. Adopt a standing rule that any supplier averaging over 3 days late gets an automatic two-week buffer. | Protects the opening-weekend selling days on both at-risk SKUs, valued at the Austin margin rate, while paying expedite only if a trigger fires. | Requires cross-functional coordination; final cost stays quote-based until a trigger fires. | APPROVE
Recommendation: Approve Option C, and treat confirming the required in-store date as the first action. Every downstream date, order-by, buffer, expedite trigger, and staffing plan, is calculated from it, and it is the one input no document in any department currently provides.